## Milestone Trend Analysis
Milestone / Reporting Date | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01
M1: Start of Project | 2009-03-03 | 2009-03-03 | 2009-03-03 | 2009-03-03 | 2009-03-03 | 2009-03-03 | 2009-03-03 | 2009-03-03
M2: Project setup completed | 2009-03-26 | 2009-04-01 | 2009-04-01 | 2009-04-02 | 2009-04-02 | 2009-04-02
M3: Detailed Planning Approved | 2009-04-24 | 2009-04-24 | 2009-04-23 | 2009-04-23 | 2009-04-23 | 2009-04-23
M4: Release for final acceptance | 2009-07-10 | 2009-07-10 | 2009-07-10 | 2009-07-24 | 2009-07-24 | 2009-08-03
M5: Final acceptance | 2009-08-20 | 2009-08-20 | 2009-08-20 | 2009-09-11 | 2009-09-11 | 2009-09-25
M6: Project closure | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31
Demand Clarification - PM(i)010 demand clarified
Project Profiling - PM(i)020 Project candidate confirmed
Project Definition - PM(i)040 Project defined
Project Agreement - PM(i)070 Project agreed
Project Handover - PM(i)080 Start of Project
Project Opening and Clarification - PM(i)100 Project setup completed
Detailed Planning - PM(i)200 Approval of detailed planning
Implementation - PM(i)600 Release for final acceptance
Acceptance - PM(i)650 Final acceptance
Project Closure - PM(i)700 Project closure

## Cost Trend Analysis
Costs / Reporting Date | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01
Overall Project Budget | 225000 | 225000 | 225000 | 225000 | 225000 | 225000
Accumulated Costs | 612 | 14581 | 34019 | 41925 | 143172.51 | 175596.42
Forecast Project Budget | 225000 | 225000 | 225000 | 225000 | 225000 | 225000