## jun 12
MINUTES OF 8th MANAGEMENT MEETING
PT. Azbil Berca Indonesia |  |  | Attendants : MS,SM, IS, IM, BS, MH, RD, YH, HW, AB, TR, TS, JS, JT, WS, SN
Monday, 16 Sept 2013 |  |  | Absentee : SH, RF, SP, IA, AH, YP, NJ, BJ, TW, HS, AJ
No | Subject | Description / Explanation | Further action & responsibility | Due date | Remarks
1 | Result until Sept | Booking : 155.693 Billion Rp. Sales : 120.142 Billion Rp. | As ABID performance for Sept could not achieve the target, Management should re-budgeting the Booking and Sales for Oct
| Sept Result | Total Booking BA&AA in Sept'13 has reached 24.403 Billion IDR | Oct prospect's is 33.325 Billion IDR, meanwhile after re-budget should reach 46.776 Billion IDR
|  | Total Sales BA&AA in Sept'13 has reached 15.457 Billion IDR | Oct prospect's is 25.850 Billion IDR, meanwhile after re-budget should reach 54.353 Billion IDR
|  | GP Rate in Sept surplus 6.798 Billion IDR | Oct prospect's is 5.181 Billion IDR, meanwhile after re-budget should reach 11.449 Billion IDR
|  | Although Booking and Sales prospect for Oct could be achieved, we still have | Conduct special meeting twice a month starting October to monitoring Booking and Sales | Oct. 21 | For AA
|  | outstanding |  | Oct. 22 | For BA
2 | Review of AAD | Ammonia Plant project is still under negotiation as they need same size application of Azbil reference | ABID would not get profit although we get this project. But ABID needs this project for reference in other fertilizer project in the future
3 | Review of | Report of BA Landmark Building use Sales Strategic Plan : | Submit Target Job List with Grade A for BA, AA, LA, NB until Dec 2013 (updated)
| BAD | - Signature Tower | Will be sent by e-mail directly to MS | HW
|  | - Terminal 3, Soeta | Open tender in Dec | WS
|  | Wish to put Azbil logo for smart hotel automation | Looking for some new hotel projects | TR
|  | Improve ABID engineering | Conducted Product and General training for 2013/2014 scheduled by TW | TW
4 | Review of LA | ABID got project from Ferron amount to 1.7 million Euro with 35% profit
So many project prospects in 2014
5 | Review of NBD | Making business plan for NBD
6 | Review of | Calculation Methods of allowance for bad debts | ABID proposed the calculation of amount of the allowance by using standard of Doubtful | Sept 15 | Roni
| Finance |  | Account and Bankcrupty Account which follows Azbil Japan standard and adopted by most of | Sept 13 | BS
Azbil Asian subsidiaries
|  | Calculation standard proposed by ABID compared in the Table of Azbil Companies | Meeting with CCM on Aug 27, need updated status oollection | ASAP | JS & HW
calculation standard
6 | Review of | Request to protect company asset
| HR & GA | Specify signature e-mail to be used for ABID employees | Assign someone to design | TS
|  | ABID will have 7 new comers in Nov; 5 persons from SBY as Sales Engineer | 6 person will be placed in Jkt, 1 person in Sby
|  | and 2 persons from Medan as @account manager | Grade for @Account Manager will be grade 8
7 | Review of | Software for Sales Support | will be presented next week | Oct. 22 | BS
| Management | Improve sales activity | Keep the existing customers, develop new customers/segment market/area |  | Sales
|  | CSR program | Education of Automatic Basic Control, OJT and Demo Unit Panel | 4Q'13 or | 1Q 2014- JF
|  | SBU Business Plan 2014 | to be submitted on nov 1 (the latest)
|  | New profit calculation formula will be implemented in 2014 | Sales (group) or @ account manager will get incentives fee based on OP performance
Project Manager (engineering) will get incentive fee based on project and GP
|  | Auditor from IBQ will visit ABID | Will interview managers of accounting, sales control and GA | Nov. 20-22
|  | ABID will participate in IPEX 2013 | Introduce Telstar under Azbil Group, Increasing selling of Robatherm and BMS | Oct.30 to | Nov.2